## Feedback Implementation
# | Area | Owner | Feedback Item | Status | Implementation Summary
Login & Dashboard
1 | Login & Dashboard | MM | Login URL redirect error After login, users were redirected to an incorrect URL instead of the page they originally requested. | Complete | The login route now captures request.args.get('next') and stores it in the session. After successful authentication, the user is redirected to the stored URL. A security validation ensures the 'next' URL starts with '/' to prevent open redirect attacks.
2 | Login & Dashboard | MM | Dashboard job links go to portal Job title links on the dashboard were pointing to public portal URLs instead of internal staff routes. | Complete | Dashboard job title links now use the engagement_job_detail internal route instead of the public token-based URL. Staff users are taken directly to the internal job management page.
Placements
3 | Placements | CW | CSV £ formatting (Â£350) Exporting placements to CSV produced garbled currency symbols (Â£ instead of £) when opened in Excel. | Complete | The CSV export now prepends a UTF-8 BOM (\ufeff) to the output stream. This signals to Excel that the file uses UTF-8 encoding, ensuring pound signs and other special characters render correctly.
4 | Placements | CW | CSV split name/email The CSV export combined associate name and email into a single column. | Complete | The placements CSV now exports 'Associate Name' and 'Associate Email' as two separate columns, allowing proper sorting and filtering in spreadsheets.
5 | Placements | CW | Name filter shows non-active placements The associate name filter dropdown included names from ended/inactive placements. | Complete | The name filter now uses an active_placement_base subquery that only includes associates with currently active placements (status signed/completed, end date in future or null). The dropdown is populated exclusively from this filtered set.
6 | Placements | CW | Client filter shows non-active placements The client filter dropdown included clients with no active placements. | Complete | The client filter uses the same active_placement_base subquery, ensuring only clients with at least one active placement appear in the dropdown.
7 | Placements | CW | On-Contract end date actions There was no way to extend or set end dates for on-contract placements in bulk. | Complete | A 'Bulk End Date' modal was added to the placements page with a date picker and multi-select. This submits to /api/contracts/bulk-extend which updates end dates on selected records and logs each change to the audit trail.
8 | Placements | MM | Forecast graphs above table Forecast headcount charts were positioned below the data table, requiring scrolling. | Complete | The forecasted headcount chart (with 1M/3M/6M/12M toggle buttons) is now rendered above the on-contract table, giving immediate visibility to trend data before the detailed listing.
9 | Placements | MM | Client summary to Revenue tab The client summary daily rate card was on the placements page where it didn't belong. | Complete | The client summary section (daily rates, margin, headcount per client) was removed from placements and relocated to the Revenue tab alongside other financial reporting.
10 | Placements | MM | Associate name links across app Associate names in placement lists were plain text with no way to navigate to their profile. | Complete | Associate names are now clickable links across all placement sub-views (on-contract, joiners, leavers, workflow) that navigate to the candidate profile page.
Workflow
11 | Workflow | MM | New apps land in Pipeline New applications were not appearing in the correct starting column of the workflow board. | Complete | The Application model defaults status to 'New', which maps to the Pipeline stage in the workflow. All new applications start in the first column regardless of source.
12 | Workflow | MM | Vetting SLA click-through The vetting summary showed SLA status but there was no way to drill down into individual candidates. | Complete | The vetting summary now displays 'All', 'In SLA', and 'Out of SLA' filter buttons. Each candidate row is clickable and links to their profile. SLA is calculated from the first vetting check creation date.
13 | Workflow | MM | AI Summary/Score quality AI-generated summaries and scores were generic and not useful for recruitment decisions. | Complete | AI prompts were rewritten for GPT-4o-mini with recruitment-specific instructions. Scoring uses a blended approach (skills match, experience, qualifications, availability). Summaries highlight strengths, concerns, and a hiring recommendation. Graceful fallback when no API key is configured.
14 | Workflow | MM | View Job bad URL The 'View Job' link in workflow cards pointed to an incorrect or broken URL. | Complete | The View Job link now uses conditional routing — if the job has an engagement, it links to engagement_job_detail; otherwise it links to the standalone job view.
15 | Workflow | MM | Manual vetting trigger + automation There was no way to manually start the vetting process, and no automation toggle. | Complete | A 'Start Vetting' button calls /api/vetting/trigger which initialises all required checks to 'In Progress', moves the application to 'Vetting In-Flight', and auto-submits to Verifile if configured. Each check has an automation_enabled toggle.
16 | Workflow | MM | Vetting status doesn't save Updating a vetting check status on the candidate profile did not persist to the database. | Complete | The vetting form action was corrected to point to the update_vetting_check route. The route properly updates the VettingCheck record, sets completed_at when 'Complete', and commits with audit logging.
17 | Workflow | MM | Vetting complete controls Candidates could be moved to 'Ready to Contract' with incomplete vetting checks. | Complete | The workflow now blocks advancement to 'Ready to Contract' unless all vetting checks are Complete, N/A, or Referral Approved. An error shows the count (e.g. '8/12 checks complete'). REFERRAL APPROVED was added as a valid completion status.
18 | Workflow | CW | Horizontal scroll from nav edge The workflow board caused unwanted horizontal scrolling past the navigation edge. | Complete | CSS overflow-x: auto was applied to the workflow card container, with margin/padding adjustments to keep the board within the viewport while allowing horizontal scroll only within the kanban area.
19 | Workflow | CW | Focus View Users wanted to hide workflow columns they weren't currently working with. | Complete | Column visibility checkboxes were added above the workflow board. Each checkbox corresponds to a stage column. Unchecking hides that column via JavaScript. Selection persists during the session.
20 | Workflow | CW | Rejected/Withdrawn to right end The Rejected/Withdrawn column was in the middle of the workflow, disrupting the progression. | Complete | Workflow stages reordered: Pipeline, Screening, Interview, Offer, Accepted, Vetting In-Flight, Ready to Contract, Contract Sent, Rejected/Withdrawn (9th and final).
21 | Workflow | CW | Contract Sent link to placement Cards in 'Contract Sent' had no way to navigate to the associated placement. | Complete | A 'View Placements' link was added to workflow cards in the Contract Sent stage, linking to the placements page filtered for that candidate/engagement.
22 | Workflow | CW | Summary modules respect filters Unsigned contracts and vetting summary showed all-time data regardless of active filters. | Complete | Both the unsigned contracts query and vetting summary now apply the same grid filters (engagement, job, date range) as the main workflow table. Summaries update when filters change.
23 | Workflow | KM | Remove Placed column The 'Placed' column was redundant since placement is tracked via Contract Sent/Signed. | Complete | Workflow reduced from 10 stages to 9 by removing the 'Placed' stage. Progression goes directly from Contract Sent to completion.
24 | Workflow | KM | Bulk Rejection with email Rejecting multiple candidates individually was time-consuming with no notification. | Complete | A 'Bulk Reject' modal allows multi-select of candidates. On submission, all selected applications move to Rejected/Withdrawn and a rejection email is sent to each candidate. Action is audit-logged.
Projects / Engagements
25 | Projects / Engagements | CW | Infographic tiles adjust with filters Summary tiles did not update when filters were applied. | Complete | A recalcSummaryTiles() JavaScript function recalculates all tile values based on currently visible (filtered) rows, triggered on every filter change.
26 | Projects / Engagements | CW | Separate Pipeline/Engagement filters Pipeline and Engagements shared a single filter bar, causing confusion. | Complete | Page restructured: Engagements section above Pipeline, each with its own independent filter bar. Engagement filters control engagement cards; Pipeline filters control opportunity cards.
27 | Projects / Engagements | CW | Closed Won auto-move Moving an opportunity to 'Closed Won' did not create an engagement. | Complete | Dragging to Closed Won auto-creates a new Engagement linked to the opportunity's client, copies relevant fields, generates a reference number, and flashes a confirmation with a link.
28 | Projects / Engagements | CW | Closed Won/Lost as tiles Closed Won/Lost were kanban columns taking up board space for rarely-accessed items. | Complete | Closed Won and Lost now display as clickable summary tiles above the board (count + total value). Clicking expands a detail list. No longer drag-target columns.
29 | Projects / Engagements | CW | Delivery Plan role filters The Delivery Plan table had no way to filter by role type. | Complete | A dp-role-filter dropdown was added above the Delivery Plan table. Selecting a role type filters rows; 'All Roles' resets.
30 | Projects / Engagements | CW | Edit Plan prompts job creation After adding new roles to a Delivery Plan, users had to manually create jobs. | Complete | When saving, the system detects roles without corresponding jobs and flashes 'Create jobs now' with a direct link to job creation pre-filled with engagement context.
31 | Projects / Engagements | MM | Job creation internal route Job creation from engagement context routed through the public portal. | Complete | Job creation uses internal Flask routes (url_for('job_form')) with engagement ID as context, keeping users within the staff portal.
32 | Projects / Engagements | MM | Edit after Closed Won Engagements created from Closed Won opportunities could not be edited. | Complete | The engagement edit route has no status-based restrictions. All engagements can be edited regardless of origin or current status.
33 | Projects / Engagements | MM | Naming convention OS001 Engagement references used prefix 'EG' which was not client-branded. | Complete | Reference generator updated to prefix 'OS' with zero-padded width 3 (OS001, OS002, OS003...) matching the client's convention.
34 | Projects / Engagements | MM | Start/end dates showing Engagement start and end dates were not visible on the projects page. | Complete | Start and end dates are now displayed in DD/MM/YYYY format on each engagement card.
35 | Projects / Engagements | MM | Weighted value updates on drag Dragging an opportunity to a new stage did not recalculate weighted value. | Complete | A STAGE_PROBABILITY map (Qualify=20%, Proposal=50%, Negotiate=75%, Closed Won=100%) auto-updates probability and weighted value on drag.
36 | Projects / Engagements | KM | Active/Completed toggle No way to separate active engagements from completed ones. | Complete | Three filter buttons: 'Active' (default), 'Completed', 'All'. Active shows in-progress engagements; Completed shows ended; All shows everything.
37 | Projects / Engagements | MM | Vetting requirements flow to workflow Vetting requirements set on an engagement did not carry through to the vetting process. | Complete | Engagement forms include 12 vetting check checkboxes stored as JSON. When vetting triggers, checked items go to 'In Progress' and submit to Verifile; unchecked items are marked 'N/A' with 'Not required for this engagement'.
Resource Pool
38 | Resource Pool | CW | Search case sensitivity Searching for candidates was case-sensitive ('john' wouldn't find 'John'). | Complete | All resource pool search queries use SQLAlchemy's .ilike() operator instead of .like(), making name, email, skills, and location searches case-insensitive.
39 | Resource Pool | CW | Advanced filters collapsed The advanced filter panel was always expanded, overwhelming users. | Complete | The panel uses Bootstrap's collapse class and is hidden by default. Users click 'Advanced Filters' to expand/collapse.
40 | Resource Pool | CW | Boolean search TypeError Using Boolean operators (AND/OR/NOT) caused a Python TypeError crash. | Complete | Changed 'if combined and not_conditions' to 'if combined is not None and not_conditions'. This handles empty SQLAlchemy clauses (falsy but not None) correctly.
41 | Resource Pool | CW | Shortlist → Add to Pipeline The 'Shortlist' button didn't clearly indicate what action was being taken. | Complete | Replaced with an 'Add to Pipeline' dropdown for selecting engagement/job. Creates a new Application with status 'Pipeline', placing the candidate directly into the workflow.
42 | Resource Pool | KM | Delete button removed from main Delete button on the resource pool table was too accessible, risking accidental deletion. | Complete | Delete removed from main table. Candidate deletion is now admin-only within the individual candidate profile page.
43 | Resource Pool | MM | Column header filters No way to quickly filter the table by status or location. | Complete | Dropdown filters added to Status and Location column headers. Selecting a value triggers applyColumnFilter() for instant client-side filtering.
44 | Resource Pool | MM | Activity feed past interview Candidate activity feed was missing stage change history. | Complete | Activity feed now runs two queries: stage changes (note_type='activity', limit 20) and general notes (limit 10). Stage changes have a distinct icon and are differentiated from manual notes.
Associate Profile
45 | Associate Profile | MM | Manual application for roles No way for staff to manually add a candidate to a job pipeline. | Complete | 'Add to Pipeline' button on resource pool and candidate profile links to /add-to-pipeline. Staff select engagement and job; a new Application is created with status 'Pipeline'.
46 | Associate Profile | CW | Status linked to placements Candidate status did not update when placed on an active assignment. | Complete | When an application moves to placed/contract signed, status auto-sets to 'On Assignment'. Also checked on profile load — active placement existence is reflected in status.
47 | Associate Profile | CW | Edit core details No way to edit a candidate's basic information from their profile. | Complete | 'Edit Details' modal added with fields for name, email, and phone. Changes save via POST with audit logging.
48 | Associate Profile | CW | Notes saving Adding a note failed silently — not saved to database. | Complete | CandidateNote creation fixed: field name corrected to content= (not note=), matching the model column. Notes now save and appear immediately.
49 | Associate Profile | CW | Active placement display Candidate profile did not show active placement information. | Complete | 'Placements' card added showing all history. Active placements display green 'Active' badge with engagement, job title, dates. Ended placements show grey 'Ended' badge.
Associate Portal
50 | Associate Portal | MM | QR code on registration 2FA setup during registration did not display a QR code, requiring manual secret entry. | Complete | QR generation uses qrcode library to create TOTP provisioning URI as scannable image. Fallback to external QR API if library fails. CSP headers updated for data: URI inline display.
Revenue
51 | Revenue | MM | Forecast vs actual margin graph No visual comparison between forecasted and actual margin figures. | Complete | marginVsForecastChart canvas added with two Chart.js series: forecast_margin and actual_margin plotted over time with distinct colours for at-a-glance comparison.
52 | Revenue | CW | Date filters apply to infographic Revenue infographic tiles showed all-time totals regardless of date range. | Complete | KPI calculations and trend data are now filter-aware. When date filters are applied, all values (revenue, margin, headcount, average rate) recalculate for the filtered period only.
53 | Revenue | CW | Cascading client/engagement filters Selecting a client did not narrow the engagement dropdown. | Complete | cascadeClientToEngagement() JS function filters the engagement dropdown to only show engagements for the selected client. 'All Clients' resets to show all.

## Summary
Area | Items | Status
Login & Dashboard | 2 | All complete
Placements | 8 | All complete
Workflow | 14 | All complete
Projects / Engagements | 13 | All complete
Resource Pool | 7 | All complete
Associate Profile | 5 | All complete
Associate Portal | 1 | All complete
Revenue | 3 | All complete
TOTAL | 53 | All complete