## Requirements
Req ID | Source Document | Document Date | Category | Requirement Description | Priority | Status | Implementation Summary | Notes
REQ-001 | OS1Feedback.xlsx | 10 Mar 2026 | Login | Login URL redirect bug — goes to 'bad URL' page first | High | Complete | Fixed empty next URL redirect bug in login route
REQ-002 | OS1Feedback.xlsx | 10 Mar 2026 | Dashboard | Job links go to website portal instead of internal job details | High | Complete | Job title links now route to internal application detail page
REQ-003 | OS1Feedback.xlsx | 10 Mar 2026 | Placements | CSV export encoding — Pay/Bill rate shows as 'GBP350' | Medium | Complete | Added UTF-8 BOM prefix for Excel compatibility
REQ-004 | OS1Feedback.xlsx | 10 Mar 2026 | Placements | CSV export — split Associate Name and Email into separate columns | Medium | Complete | Split into separate Name and Email columns
REQ-005 | OS1Feedback.xlsx | 10 Mar 2026 | Placements | Name filter shows associates without active placements | Medium | Complete | Filter now only shows associates with active placements
REQ-006 | OS1Feedback.xlsx | 10 Mar 2026 | Placements | Client filter includes clients without active placements | Medium | Complete | Filter now only includes clients with active placements
REQ-007 | OS1Feedback.xlsx | 10 Mar 2026 | Placements | On Contract module needs actions — ability to change end date | Medium | Complete | Added end date change functionality on contract view
REQ-008 | OS1Feedback.xlsx | 10 Mar 2026 | Placements | Forecasted headcount graphs should be above on-contract list | Medium | Complete | Forecast chart moved above on-contract list
REQ-009 | OS1Feedback.xlsx | 10 Mar 2026 | Placements | Client Summary daily rate card visible to non-admins | Medium | Complete | Client Summary daily rate card removed from this view
REQ-010 | OS1Feedback.xlsx | 10 Mar 2026 | Placements | Associate names should be clickable to open profile | Medium | Complete | Associate names now link to candidate profile everywhere
REQ-011 | OS1Feedback.xlsx | 10 Mar 2026 | Workflow | New applications land in Shortlisted instead of Pipeline | High | Complete | New applications now land in Pipeline stage
REQ-012 | OS1Feedback.xlsx | 10 Mar 2026 | Workflow | No option to click into vetting checks to see associates outside SLA | Medium | Complete | Vetting summary with SLA tracking added
REQ-013 | OS1Feedback.xlsx | 10 Mar 2026 | Workflow | AI summary copies first role verbatim; AI score not working | Medium | Complete | AI summary and scoring logic fixed
REQ-014 | OS1Feedback.xlsx | 10 Mar 2026 | Workflow | View Job button goes to bad URL | High | Complete | View Job link fixed to internal route
REQ-015 | OS1Feedback.xlsx | 10 Mar 2026 | Workflow | Need manual button to trigger vetting to In Progress | High | Complete | Start Vetting button added with auto-check creation + email | Contradiction #1 resolved
REQ-016 | OS1Feedback.xlsx | 10 Mar 2026 | Workflow | Vetting check status updates don't save | High | Complete | Vetting form action fixed to update_vetting_check route
REQ-017 | OS1Feedback.xlsx | 10 Mar 2026 | Workflow | Workflow lets you tick vetting complete without all checks done; need REFERRAL status | High | Complete | Blocking rule: all checks must be Complete/N/A before Ready to Contract. REFERRAL APPROVED status added.
REQ-018 | OS1Feedback.xlsx | 10 Mar 2026 | Workflow | Horizontal scroll should start at edge of left nav; left panel fixed | Medium | Complete | Fixed horizontal scroll with sticky left nav panel
REQ-019 | OS1Feedback.xlsx | 10 Mar 2026 | Workflow | Focus View — allow users to limit workflow grid columns | Medium | Complete | Focus View with column checkboxes implemented
REQ-020 | OS1Feedback.xlsx | 10 Mar 2026 | Workflow | Rejected/Withdrawn column should be at right-hand end | Low | Complete | Rejected/Withdrawn moved to last column position
REQ-021 | OS1Feedback.xlsx | 10 Mar 2026 | Workflow | Placed/Contract Sent — add link to OS1 placement | Medium | Complete | Contract Sent shows 'View Placements' link
REQ-022 | OS1Feedback.xlsx | 10 Mar 2026 | Workflow | Unsigned Contracts & Vetting Summary should respond to grid filters | Medium | Complete | Both modules now filter-responsive to grid selections
REQ-023 | OS1Feedback.xlsx | 10 Mar 2026 | Workflow | Placed column — remove from workflow grid | Medium | Complete | Placed column removed; signed contracts move to Placements section
REQ-024 | OS1Feedback.xlsx | 10 Mar 2026 | Workflow | Bulk rejection with email notification when role is filled | Medium | Complete | Bulk reject modal with email notification implemented
REQ-025 | OS1Feedback.xlsx | 10 Mar 2026 | Projects | Four infographic tiles should adjust based on page filters | Medium | Complete | Summary tiles now respond to applied page filters
REQ-026 | OS1Feedback.xlsx | 10 Mar 2026 | Projects | Filters only filter Engagements list, not Pipeline/Opportunities | Medium | Complete | Separate filter bars for Engagements and Pipeline/Opportunities
REQ-027 | OS1Feedback.xlsx | 10 Mar 2026 | Projects | Closed Won should auto-move from Pipeline to Current Engagements | High | Complete | Closed Won auto-moves to Current Engagements on drag
REQ-028 | OS1Feedback.xlsx | 10 Mar 2026 | Projects | Closed Won/Lost should be clickable tiles, not kanban columns | Medium | Complete | Removed from kanban columns; shown as clickable summary tiles above kanban. Procurement cards have Won/Lost action buttons that auto-move and create engagement on Won.
REQ-029 | OS1Feedback.xlsx | 10 Mar 2026 | Projects | Engagement main page — no filters on Delivery Plan by Role table | Medium | Complete | Role and Intake filters added to Delivery Plan table
REQ-030 | OS1Feedback.xlsx | 10 Mar 2026 | Projects | Adding new role to plan doesn't create matching Active Job Post | Medium | Complete | Engagement edit plan now prompts to create matching job
REQ-031 | OS1Feedback.xlsx | 10 Mar 2026 | Projects | Creating a job went to broken web page; define vetting requirements at setup | High | Complete | Job creation fixed; vetting requirements textarea on engagement
REQ-032 | OS1Feedback.xlsx | 10 Mar 2026 | Projects | Cannot amend project name after creation | Medium | Complete | Edit engagement page created with name amendment
REQ-033 | OS1Feedback.xlsx | 10 Mar 2026 | Projects | Use convention OS001, OS002, OS003 for project references | Low | Complete | Engagement ref prefix changed from EG to OS (OS001, OS002...)
REQ-034 | OS1Feedback.xlsx | 10 Mar 2026 | Projects | Start/end dates not showing in Current Engagements after Closed Won | Medium | Complete | Start/end dates now display correctly after status change
REQ-035 | OS1Feedback.xlsx | 10 Mar 2026 | Projects | Weighted forecast doesn't update when moving through card stages | Medium | Complete | Opportunity probability auto-updates per pipeline stage
REQ-036 | OS1Feedback.xlsx | 10 Mar 2026 | Projects | Add toggle filter for Active vs Completed engagements | Medium | Complete | Active/Completed/All toggle filter with default to Active
REQ-037 | OS1Feedback.xlsx | 10 Mar 2026 | Resource Pool | Search for KYC returns results but quoted 'KYC' returns zero | High | Complete | Quote stripping on search queries fixed
REQ-038 | OS1Feedback.xlsx | 10 Mar 2026 | Resource Pool | Advanced filters auto-expand on page refresh | Low | Complete | Filters collapsed by default on page load
REQ-039 | OS1Feedback.xlsx | 10 Mar 2026 | Resource Pool | Boolean search CDD OR KYC OR AML returns TypeError | High | Complete | Boolean search condition logic fixed
REQ-040 | OS1Feedback.xlsx | 10 Mar 2026 | Resource Pool | Shortlist button unclear — change to 'Add to' with job pipeline | Medium | Complete | Replaced with 'Add to Pipeline' dropdown
REQ-041 | OS1Feedback.xlsx | 10 Mar 2026 | Resource Pool | Delete button on main page — remove, admin-only in profile | Medium | Complete | Delete removed from main table; admin-only in profile
REQ-042 | OS1Feedback.xlsx | 10 Mar 2026 | Resource Pool | Should be able to filter by table headings (status, location) | Medium | Complete | Status and Location column header filters added
REQ-043 | OS1Feedback.xlsx | 10 Mar 2026 | Resource Pool | Activity feed doesn't log past interview stage | Medium | Complete | Activity notes auto-created for all workflow moves
REQ-044 | OS1Feedback.xlsx | 10 Mar 2026 | Resource Pool | No way to manually add associate to a job process | Medium | Complete | Manual application for roles functionality added
REQ-045 | OS1Feedback.xlsx | 10 Mar 2026 | Associate Profile | Profile status should auto-link to placements | Medium | Complete | Status auto-linked to active placements
REQ-046 | OS1Feedback.xlsx | 10 Mar 2026 | Associate Profile | No option to update core details (email, name, phone) | High | Complete | Edit Details modal for name/email/phone added
REQ-047 | OS1Feedback.xlsx | 10 Mar 2026 | Associate Profile | Cannot add Activity or save General Notes | High | Complete | General Notes card with scrollable list; CandidateNote field fixed
REQ-048 | OS1Feedback.xlsx | 10 Mar 2026 | Associate Profile | Active placement not showing for certain associates | High | Complete | Active placement display logic fixed
REQ-049 | OS1Feedback.xlsx | 10 Mar 2026 | Associate Portal | QR code not showing during 2FA registration | High | Complete | QR code generates inline base64 with API fallback; CSP updated
REQ-050 | OS1Feedback.xlsx | 10 Mar 2026 | Revenue | Add forecasted margin vs actual margin graph | Medium | Complete | Forecast Margin vs Actual Margin chart added with trend data
REQ-051 | OS1Feedback.xlsx | 10 Mar 2026 | Revenue | Date filters don't apply to Actual vs Forecast Revenue infographic | Medium | Complete | Filter-aware trend data generation respects date range
REQ-052 | OS1Feedback.xlsx | 10 Mar 2026 | Revenue | Filters don't have cascading relationship (client→engagement) | Medium | Complete | Cascading Client → Engagement filter implemented
REQ-053 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Consent form — associates must sign before vetting checks | High | Complete | Digital consent form built with e-signature in portal
REQ-054 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | No vetting checks can be submitted without completed Consent Form | High | Complete | Blocking rule: consent required before vetting proceeds | Contradiction #3 also covers this
REQ-055 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Consent form auto-attached to all reference requests | Medium | Complete | send_reference route queries consent_signed Document, reads file, passes as email attachment | Consent PDF auto-attached to all outgoing reference request emails
REQ-056 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Declaration Yes/No form with auto On Hold when vetting exists | High | Complete | 6-question declaration form; Yes → On Hold for all vetting checks if grid exists, else flags candidate | Contradiction #3 resolved
REQ-057 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Client-specific document config per project/engagement | High | Complete | required_documents JSON field on Engagement model
REQ-058 | Vetting Section (Word).docx | 04 Mar 2026 | Documents | Proof of ID must be in-date; expiry tracked; linked to DBS | High | Complete | expiry_date field on Document model; daily expiry check job
REQ-059 | Vetting Section (Word).docx | 04 Mar 2026 | Documents | Proof of Address with 90-day rule enforcement | High | Complete | _check_poa_90_day_rule() helper function enforces 90-day limit
REQ-060 | Vetting Section (Word).docx | 04 Mar 2026 | Documents | Right to Work expiry tracking during assignment | High | Complete | expiry_date on Document model; daily expiry alerts via scheduler
REQ-061 | Vetting Section (Word).docx | 04 Mar 2026 | References | Reference requirements client-specific (X years configurable) | High | Complete | reference_period_years on Engagement; default 3; editable in engagement forms | Contradiction #5 resolved
REQ-062 | Vetting Section (Word).docx | 04 Mar 2026 | References | All gaps over X days must be explained | High | Complete | Portal gap detection with >90 day threshold and evidence upload
REQ-063 | Vetting Section (Word).docx | 04 Mar 2026 | References | System blocks progression if employment history incomplete | Medium | Complete | _check_employment_complete() validates gaps >90 days are explained; vetting progress shows warning | P10 — enforcement via helper function
REQ-064 | Vetting Section (Word).docx | 04 Mar 2026 | References | Reference contact auto-populate from approved contacts list | High | Complete | Portal autocomplete from ReferenceContact table + admin CRUD import
REQ-065 | Vetting Section (Word).docx | 04 Mar 2026 | References | Flagged reference house auto-warning on entry | High | Complete | Portal real-time check + admin CRUD with full intel display
REQ-066 | Vetting Section (Word).docx | 04 Mar 2026 | References | Unknown referee email requires manual check before sending | Medium | Complete | Unknown company → pending_verification amber warning
REQ-067 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Vetting statuses: Waiting for Associate, Ready to Start, In Progress, On Hold, Awaiting QC, QC Complete | High | Complete | All statuses supported in VettingCheck model and routes
REQ-068 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Cards auto-move based on triggers (vetting complete → Contract Issued) | High | Complete | Auto-move when all 12 checks complete
REQ-069 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Cards manually moveable with permission controls | High | Complete | Analyst cannot QC checks assigned to themselves (N9)
REQ-070 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Per-check colour system: White/Green/Orange — auto and manual | High | Complete | colour + colour_manual fields; /action/set-check-colour route
REQ-071 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Prompt-only checks (no upload required) | Medium | Complete | prompt_only field on VettingCheck model
REQ-072 | Vetting Section (Word).docx | 04 Mar 2026 | References | Reference cards: associate data, permission status, sent timestamp, .msg upload | High | Complete | ReferenceRequest model with all fields; send/chase/receive routes
REQ-073 | Vetting Section (Word).docx | 04 Mar 2026 | References | Reference timeline visual with gap detection after refs received | High | Complete | Portal employment timeline with >90 day gap detection
REQ-074 | Vetting Section (Word).docx | 04 Mar 2026 | References | Send Reference email route to referee | High | Complete | /action/send-reference route with email
REQ-075 | Vetting Section (Word).docx | 04 Mar 2026 | References | Chase Reference route — resend with Reminder, max 3 then flag | High | Complete | /action/chase-reference with chase_count; max 3 → On Hold
REQ-076 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Auto-chase references every 72 hours | High | Complete | APScheduler job: auto_chase_references every 72h
REQ-077 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Auto-poll Verifile every 24 hours for pending checks | High | Complete | APScheduler job: auto_poll_verifile every 24h
REQ-078 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Auto-chase candidates every 24 hours for incomplete profiles | Medium | Complete | APScheduler job: auto_chase_candidates every 24h
REQ-079 | Vetting Section (Word).docx | 04 Mar 2026 | Documents | Document expiry daily alerts (30-day warning + expired notes) | High | Complete | APScheduler job: check_document_expiry daily; CandidateNote created
REQ-080 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | QC workflow: submit for QC, approve, reject | High | Complete | 3 routes: submit-for-qc, qc-approve, qc-reject
REQ-081 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Analyst case allocation with staff dropdown + filter | High | Complete | assigned_to field; assign-analyst route; workflow filter dropdown
REQ-082 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | ID verified via video call/in-person/IDVT before DBS submission | High | Complete | id_verified + id_verification_method fields; /action/verify-id route
REQ-083 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Grid removal when vetting complete + contracted + start date passed | Medium | Complete | _should_remove_from_grid() helper function
REQ-084 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | NI Number field on candidate/associate | High | Complete | national_insurance_number on AssociateProfile model in portal
REQ-085 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Gender field on candidate model | High | Complete | gender field on Candidate model in app.py
REQ-086 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Mother's Maiden Name, DL Number, Passport Number (optional DBS fields) | Medium | Complete | mothers_maiden_name, driving_licence_number, passport_number on Candidate
REQ-087 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Citizenship and Place of Birth fields | High | Complete | citizenship, place_of_birth on Candidate model
REQ-088 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Work Location for World Check | Medium | Complete | work_location field on Candidate model
REQ-089 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Name variations tracking (multiple name forms for checks) | Medium | Complete | name_variations JSON field on Candidate model
REQ-090 | Vetting Section (Word).docx | 04 Mar 2026 | Admin | Admin CRUD for approved reference contacts (4,935 entries) with CSV import | High | Complete | 5 routes + template: list, add, edit, delete, CSV import
REQ-091 | Vetting Section (Word).docx | 04 Mar 2026 | Admin | Admin CRUD for flagged reference houses with full intel display | High | Complete | 4 routes + template: list with intel cards, add, edit, delete
REQ-092 | Declaration Form.pdf | 04 Mar 2026 | Associate Portal | 6 Yes/No declaration questions (restrictions, convictions, CCJ, bankruptcy, dismissed, referencing) | High | Complete | Full form in declaration_form.html with all 6 questions + conditional detail fields
REQ-093 | Declaration Form.pdf | 04 Mar 2026 | Associate Portal | Open disclosure text box for voluntary declarations | Medium | Complete | disclosure_text field in DeclarationRecord model + textarea in form
REQ-094 | Declaration Form.pdf | 04 Mar 2026 | Associate Portal | E-signature with Legal Name, Signed Date, confirmation statement | High | Complete | DeclarationRecord: legal_name, signed_date, ip_address; confirmation checkbox
REQ-095 | Consent Form.pdf | 04 Mar 2026 | Associate Portal | Full consent text with data sharing and acknowledgment sections | High | Complete | consent_form.html with 9 acknowledgment items + data processing info
REQ-096 | Consent Form.pdf | 04 Mar 2026 | Associate Portal | Secondary employment Yes/No with job title if Yes | Medium | Complete | ConsentRecord: secondary_employment, secondary_employment_details fields
REQ-097 | Consent Form.pdf | 04 Mar 2026 | Associate Portal | Fraud prevention Cifas section in consent | Medium | Complete | Cifas fraud prevention section in consent_form.html
REQ-098 | Consent Form.pdf | 04 Mar 2026 | Associate Portal | E-signature with Legal Name, Signed Date | High | Complete | ConsentRecord: legal_name, signed_date, ip_address, consent_given
REQ-099 | Consent Form.pdf | 04 Mar 2026 | Associate Portal | Manual upload fallback for hand-signed consent forms | Medium | Complete | manual_consent file upload in consent_form POST; saves as consent_signed doc type | Contradiction #4 resolved
REQ-100 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Associate Portal | Portal dashboard with progress bars per section (Personal/Company/Background) | High | Complete | 3-section progress bars with % completion on dashboard
REQ-101 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Associate Portal | Personal details: all fields including emergency contact, DOB, aliases, salary | High | Complete | Full form: title, name, aliases, previous names, DOB, address, emergency contact, salary, NI, CV
REQ-102 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Associate Portal | Company details: umbrella panel + limited company fields + IR35 text | High | Complete | Umbrella selection (now configurable), Ltd Co fields, IR35 banner. Contradiction #6 resolved.
REQ-103 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Associate Portal | Assignment History page (Role, Project, Client, Dates, Rate, Status) | High | Complete | assignments.html table with On Contract/Contract ended status
REQ-104 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Timesheets | Timesheet Mon-Sun weekly grid with Standard/Overtime/Holiday/Sickness | High | Complete | Full weekly grid with configurable time types, half/full day dropdowns, HH:MM OT input
REQ-105 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Timesheets | Expense section with upload and type/amount | Medium | Complete | Expense add form with type/description/amount/receipt upload; delete route; totals auto-update | P6 — complete
REQ-106 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Timesheets | Previous Timesheets historical section with monthly bundles | Medium | Complete | Monthly bundle grouping with collapsible history
REQ-107 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Timesheets | Timesheet ID and Period display in summary panel | Medium | Complete | Summary panel with billable days, OT hours, amounts, totals
REQ-108 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Timesheets | Overtime rate as separate field from day rate | Medium | Complete | TimesheetConfig: day_rate + overtime_rate separate fields
REQ-109 | An Intro to Vetting.docx | 04 Mar 2026 | Documents | Acceptable POA documents with specific expiry rules (bank 90d, council tax 12m) | High | Complete | _check_poa_90_day_rule() helper; expiry_date on Document model | Staff-side enforcement complete
REQ-110 | An Intro to Vetting.docx | 04 Mar 2026 | Associate Portal | Vetting forms via e-signature with hand-signed upload fallback | High | Complete | Signable e-sign primary; manual PDF upload fallback added | Contradiction #4 resolved
REQ-111 | An Intro to Vetting.docx | 04 Mar 2026 | Associate Portal | HMRC Employment History download guidance for associates | Medium | Complete | Guidance in intro_to_vetting.html referencing accordion section
REQ-112 | An Intro to Vetting.docx | 04 Mar 2026 | Associate Portal | Alternative evidence list for missing references (payslips, P60, contracts) | Medium | Complete | Listed in intro_to_vetting.html referencing section with examples
REQ-113 | An Intro to Vetting.docx | 04 Mar 2026 | Associate Portal | Umbrella companies: Trafalgar + PayStream with contact details (configurable) | Medium | Complete | Pre-seeded in ApprovedUmbrella table; admin can add/remove; portal reads dynamically | Contradiction #6 resolved
REQ-114 | Reference Request - Contact Details.xlsx | 04 Mar 2026 | Admin | 4,935 approved reference contacts dataset with auto-populate | High | Complete | ReferenceContact model; portal autocomplete API; admin CRUD + CSV import
REQ-115 | Reference Houses - Intel.xlsx | 04 Mar 2026 | Admin | 23 flagged reference houses with full intel (website, Companies House, end clients, investigation notes) | High | Complete | FlaggedReferenceHouse model; admin CRUD cards with all intel fields
REQ-116 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Associate Portal | Vacancy detail page — /portal/vacancies/<id> | Medium | Complete | vacancy_detail route added; renders vacancy_detail.html with job data and already_applied check | P1 — complete
REQ-117 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Associate Portal | Vacancy apply route — /portal/vacancies/<id>/apply | Medium | Complete | vacancy_apply POST route creates Application with Pipeline status | P2 — complete
REQ-118 | Gap Analysis | 19 Mar 2026 | Associate Portal | Forgot password route — /portal/forgot-password | Medium | Complete | forgot_password route sends magic link (is_signup=False); anti-enumeration response | P3 — complete
REQ-119 | Gap Analysis | 19 Mar 2026 | Associate Portal | Resend verification route — /portal/resend-verification | Medium | Complete | resend_verification POST route resends magic link if account exists without password | P4 — complete
REQ-120 | Gap Analysis | 19 Mar 2026 | Associate Portal | Employment/gap entry edit functionality | Medium | Complete | references_edit_entry POST route + api_edit_entry AJAX route for editing employment/gap entries | P5 — complete
REQ-121 | Vetting Section (Word).docx | 04 Mar 2026 | Associate Portal | 5-year address history page + AddressHistory model (required for DBS/Credit checks) | High | Complete | AddressHistory model + /portal/address-history route + template with 5-year coverage progress bar | P7 — complete
REQ-122 | Vetting Section (Word).docx | 04 Mar 2026 | Associate Portal | Gender field on portal personal details form | Medium | Complete | Gender column on AssociateProfile + dropdown on personal_details.html (Male/Female/Non-binary/Prefer not to say) | P8 — complete
REQ-123 | Vetting Section (Word).docx | 04 Mar 2026 | Associate Portal | POA type-specific expiry rules in portal document upload (bank 90d, council tax 12m) | Medium | Complete | POA sub-type dropdown with expiry validation: bank/utility/credit 90 days, council tax/mortgage 12 months | P11 — complete
REQ-124 | Vetting Section (Word).docx | 04 Mar 2026 | Associate Portal | Acceptable evidence guidance text on gap entries | Low | Complete | Detailed guidance box per gap type: unemployment, travel, parental, education, career break, other — with specific evidence examples | P13 — complete
REQ-125 | Security Audit | 19 Mar 2026 | Security | Open redirect prevention on portal login/register | High | Complete | _safe_next_url() validates all redirect params; must start with / not // | S1
REQ-126 | Security Audit | 19 Mar 2026 | Security | Rate limiting on portal login (10/minute) | High | Complete | @limiter.limit('10 per minute') applied to login + register routes | S2
REQ-127 | Security Audit | 19 Mar 2026 | Security | Company document upload extension whitelist | Medium | Complete | Extension check: pdf, doc, docx, jpg, jpeg, png only | S3
REQ-128 | Security Audit | 19 Mar 2026 | Security | Profile-pic path traversal prevention | Low | Complete | Removed <path:> converter; uses <filename> only | S4
REQ-129 | Security Audit | 19 Mar 2026 | Security | Password minimum 12 characters (match staff policy) | Medium | Complete | Backend validation + frontend JS + template text updated to 12 | S5
REQ-130 | Security Audit | 19 Mar 2026 | Security | Audit logging for portal auth events | Medium | Complete | _audit_portal() logs login, failed login, logout, 2FA verify | S6
REQ-131 | Security Audit | 19 Mar 2026 | Security | Session regeneration on portal logout | Low | Complete | session.modified=True on logout to regenerate session | S7
REQ-132 | Security Audit | 19 Mar 2026 | Security | 2FA field name mismatch fix (totp_code/backup_code) | High | Complete | Routes now read totp_code + backup_code matching template field names | S8
REQ-133 | Security Audit | 19 Mar 2026 | Security | Setup session key expiry (15 min timeout) | Low | Complete | associate_setup_password_ts + associate_setup_2fa_ts with 900s check | S9
REQ-134 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | CONTRADICTION #1: Vetting trigger — auto-load requirements on project add + manual Start Vetting button | High | Complete | _auto_create_vetting_checks() creates 12 checks as WAITING FOR ASSOCIATE; /action/start-vetting changes to NOT STARTED + sends email | Resolved: both auto-load AND manual trigger
REQ-135 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | CONTRADICTION #2: 'Waiting External' status — not adding, duplicates In Progress | Low | Complete | No action needed; document itself says to skip this status | Resolved: skipped per doc recommendation
REQ-136 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | CONTRADICTION #3: Declaration auto-hold — On Hold when vetting grid exists, else flag candidate | High | Complete | Declaration Yes → queries VettingCheck; if exist → ON HOLD + orange; if not → flags candidate | Resolved: dual behaviour
REQ-137 | Consent Form.pdf | 04 Mar 2026 | Associate Portal | CONTRADICTION #4: Consent form — e-sign primary, manual upload fallback | Medium | Complete | Digital consent primary flow retained; manual_consent file upload added as fallback | Resolved: both paths supported
REQ-138 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | CONTRADICTION #5: Reference period — configurable per engagement, default 3 years | High | Complete | reference_period_years on Engagement model; editable in create/edit engagement forms; default 3 | Resolved: configurable with default
REQ-139 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Admin | CONTRADICTION #6: Umbrella companies — configurable admin panel, pre-seeded | Medium | Complete | ApprovedUmbrella model + admin CRUD; portal reads dynamically with hardcoded fallback | Resolved: configurable panel
REQ-140 | OS1Feedback.xlsx | 10 Mar 2026 | Workflow | CONTRADICTION #7: Placed column vs grid removal rules — already resolved | Low | Complete | Placed column removed per feedback; _should_remove_from_grid() for vetting workflow | Resolved: different views, no conflict
REQ-141 | Consent Form.pdf | 04 Mar 2026 | Associate Portal | Consent form text must match source: permissions for searches, consequences (3 bullets), data sharing outside EEA, HEDD/criminal/social media listed | High | Complete | Consent form Section 1 rewritten to match source PDF verbatim: permissions, consequences, data sharing, specific search types | Direct PDF comparison fix
REQ-142 | Consent Form.pdf | 04 Mar 2026 | Associate Portal | 9 fair processing bullet points from Data Protection Act 2018 displayed verbatim | High | Complete | Consent form Section 3 rewritten with all 9 original fair processing commitments from source PDF | Direct PDF comparison fix
REQ-143 | Consent Form.pdf | 04 Mar 2026 | Associate Portal | Data protection contact email on consent form fraud prevention section | Medium | Complete | compliance@optimussolutions.co.uk mailto link added to Cifas/fraud prevention section | Direct PDF comparison fix
REQ-144 | OS1Feedback.xlsx | 10 Mar 2026 | Vetting | 'Returned - Pending Check' vetting status for checks returned but not yet reviewed | Medium | Complete | Added as valid VettingCheck status; distinct from QC rejection (Ready to Start) | Third pass fix 1
REQ-145 | OS1Feedback.xlsx | 10 Mar 2026 | Projects | Auto-open engagement edit window when opportunity moved to Closed Won | Low | Complete | Pipeline drag-drop handler redirects to engagement edit page on Closed Won auto-create | Third pass fix 2
REQ-146 | OS1Feedback.xlsx | 10 Mar 2026 | Vetting | Referral Approved requires two-step approval (different user than assigned analyst) | Medium | Complete | /action/referral-approve route with assigned_to check; referral_approved_by/at fields on VettingCheck | Third pass fix 3
REQ-147 | Vetting Section (Word).docx | 04 Mar 2026 | Documents | RTW expired British passport acceptance rule (photo recognisable, not clipped) | Medium | Complete | RTW_RULES dict with expired_ok flag and conditions; /api/validate-rtw endpoint | Third pass fix 4
REQ-148 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | POA verification (video/in-person/IDVT) also required before DBS submission | Medium | Complete | DBS Check in CHECK_DATA_REQUIREMENTS now includes requires_poa_verified + proof_of_address document | Third pass fix 5
REQ-149 | Vetting Section (Word).docx | 04 Mar 2026 | References | Gap threshold days configurable per client/engagement (not hardcoded 90) | Medium | Complete | gap_threshold_days column on Engagement model (default 90); _detect_gaps accepts threshold param | Third pass fix 6
REQ-150 | Vetting Section (Word).docx | 04 Mar 2026 | References | Referee hold-until date to pause auto-chasers when referee says 'will take X days' | Medium | Complete | hold_until field on ReferenceRequest; /action/hold-reference route; auto-chase scheduler respects hold | Third pass fix 7
REQ-151 | OS1Feedback.xlsx | 10 Mar 2026 | Workflow | Client and engagement names clickable as links in workflow grid cards | Low | Complete | workflow.html card details: client/engagement names wrapped in <a> links to engagement_dashboard | Third pass fix 8
REQ-152 | An Intro to Vetting.docx | 04 Mar 2026 | Associate Portal | Privacy policy link in global portal footer (not just intro_to_vetting page) | Low | Complete | Privacy policy link + copyright added to portal base.html footer globally | Third pass fix 9
REQ-153 | OS1Feedback.xlsx | 10 Mar 2026 | Vetting | Per-check automation override toggle (stop/start API automation) | Medium | Complete | automation_enabled column on VettingCheck; toggle checkbox in application_detail.html; API toggle route | Found in third pass — already implemented
REQ-154 | OS1Feedback.xlsx | 10 Mar 2026 | Placements | Bulk end date change on placements (individual and bulk) | Medium | Complete | Bulk End Date modal in placements.html; /api/placements/bulk-end-date route | Found in third pass — already implemented
REQ-155 | OS1Feedback.xlsx | 10 Mar 2026 | Placements | Single overall headcount graph with project filter selector | Medium | Complete | combinedForecastChart with forecastEngagementFilter dropdown in placements.html | Found in third pass — already implemented
REQ-156 | OS1Feedback.xlsx | 10 Mar 2026 | Placements | Client Summary graph moved to Revenue tab (not just removed from Placements) | Medium | Complete | Revenue page contains Client Summary section with revenue/headcount charts | Found in third pass — already implemented
REQ-157 | OS1Feedback.xlsx | 10 Mar 2026 | Placements | Engagements filter scoped to engagements with active placements only | Low | Complete | Placements route queries engagements from active_placement_base subquery | Found in third pass — already implemented
REQ-158 | Vetting Section (Word).docx | 04 Mar 2026 | References | Company address as explicit reference data field in EmploymentHistory | Low | Complete | EmploymentHistory model has company_address column; used in form submissions | Found in third pass — already implemented
REQ-159 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Associate Portal | Profile picture upload on portal personal details page (optional) | Low | Complete | Profile picture upload section in personal_details.html; /portal/profile-picture route | Found in third pass — already implemented
REQ-160 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Associate Portal | CV upload button on portal personal details page | Medium | Complete | CV upload section in personal_details.html; /portal/upload-cv route | Found in third pass — already implemented
REQ-161 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Timesheets | 'Unplanned Absence' as default time type in timesheet configuration | Low | Complete | TimesheetConfig default time_types JSON includes 'Unplanned Absence' | Found in third pass — already implemented
REQ-162 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Timesheets | Full-day/Half-day dropdown selectors for time entries (not numeric input) | Medium | Complete | timesheets.html uses <select> with '-', '1/2', '1' options per day | Found in third pass — already implemented
REQ-163 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Timesheets | Cancel Timesheet button on active timesheet | Low | Complete | Cancel Timesheet button posts to /portal/timesheets/cancel with confirmation | Found in third pass — already implemented
REQ-164 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Associate Portal | Legal name guidance text: 'names as they appear on your passport' | Low | Complete | personal_details.html guidance text: 'Please enter your legal names as they appear on your passport' | Found in third pass — already implemented
REQ-165 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Associate Portal | Employment Company field auto-populated readonly from Company Details selection | Medium | Complete | personal_details.html: Employment Company readonly input populated from CompanyDetails query | Found in third pass — already implemented
REQ-166 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Timesheets | Expense backend config: toggle on/off per project, define types, set limits, disabled by default (PPT comment) | High | Complete | TimesheetConfig model with expense_enabled (default False), expense_types (JSON), expense_limits (JSON); admin config page | From PPT annotation by CW
REQ-167 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Timesheets | Time types configurable per project/role/placement in backend (PPT comment) | High | Complete | TimesheetConfig.time_types JSON column; only assigned types shown on associate timesheet; admin config page | From PPT annotation by CW
REQ-168 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Timesheets | Overtime rules configurable: enable/disable, multipliers, OT rate definition (PPT comment) | Medium | Complete | TimesheetConfig: overtime_enabled, overtime_multiplier, overtime_rate_type; admin configurable | From PPT annotation by CW
REQ-169 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Associate Portal | Limited Company only visible for outside-IR35 roles; 3 document uploads (Cert of Incorporation, PIPL, VAT cert) (PPT comment) | High | Complete | IR35 check in company_details route; allow_limited flag; 3 doc upload types in form | From PPT annotation by CW
REQ-170 | Vetting Section (Word).docx | 04 Mar 2026 | Associate Portal | Qualification fields: name, type (BSc/MSc), grade, institution, dates, permission to verify | High | Complete | QualificationRecord model with all fields; add qualification form on references page + AJAX API
REQ-171 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Per-check-type data validation: block submission if required fields incomplete (ID/POA/address history/gender per check) | High | Complete | CHECK_DATA_REQUIREMENTS dict + _validate_check_data() + /api/validate-check-data endpoint | GAP 6 — newly implemented
REQ-172 | Vetting Section (Word).docx | 04 Mar 2026 | References | Reference permission No handling: mandatory reason why + future date or TBC | Medium | Complete | EmploymentHistory model: permission_to_request, permission_delay_reason, permission_future_date; form conditional fields
REQ-173 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Vetting grid filters: Analyst, Intake Date, Client, Project, Role, Resourcing Status; sort by Intake Date primary | High | Complete | Workflow route has all 6 filter params + analyst dropdown; intake_date primary sort
REQ-174 | Vetting Section (Word).docx | 04 Mar 2026 | Documents | Document-to-project linkage: track which engagement used which document | Medium | Complete | engagement_id column on Document model; set when documents used in engagement context
REQ-175 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Associate Portal | Available From date field on personal details | Low | Complete | AssociateProfile.available_from (Date); rendered in personal_details.html form
REQ-176 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Vetting start email should reference Intro to Vetting content/link | Medium | Complete | start_vetting email links to portal dashboard; intro_to_vetting page accessible from portal nav
REQ-177 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Resource Pool | Unsubscribe must also remove associate from Resource Pool searches (PPT comment) | High | Complete | Resource Pool query now filters out candidates with unsubscribed=True on AssociateProfile | REQ-069 from PPT annotation
REQ-178 | OS1_Associate Portal_v1.0.pptx | 04 Mar 2026 | Timesheets | Edit Timesheet button must be hidden after timesheet is Approved/Submitted (PPT comment) | Medium | Complete | Timesheet buttons wrapped in status check; locked badge shown when not Draft | REQ-091 from PPT annotation
REQ-179 | Reference Request - Contact Details.xlsx | 04 Mar 2026 | References | Detect duplicate referee emails across different company names (fraud indicator) | Medium | Complete | /api/check-duplicate-referee-email endpoint returns companies sharing an email | REQ-003 from Excel conditional formatting
REQ-180 | Vetting Section (Word).docx | 04 Mar 2026 | Vetting | Umbrella registration must be confirmed before contract can be issued | High | Complete | _check_umbrella_registration() validates company details exist before contract issuance | REQ-094 + REQ-132
REQ-181 | Vetting Section (Word).docx | 04 Mar 2026 | Documents | Bulk document download for audit purposes (all candidate docs as ZIP) | Medium | Complete | /candidate/<id>/download-all-docs route creates ZIP of all documents | REQ-111
REQ-182 | Vetting Section (Word).docx | 04 Mar 2026 | References | Non-responding organisation awareness (DMS, BDO, Eversheds etc.) | Medium | Complete | NON_RESPONDING_ORGS dict + /api/check-reference-org endpoint with warnings | REQ-113
REQ-183 | Vetting Section (Word).docx | 04 Mar 2026 | References | Self-employment alternative evidence rules (Amazon Flex, Uber → bank statements) | Medium | Complete | NON_RESPONDING_ORGS includes self-employment entries with bank statement guidance | REQ-114
REQ-184 | Vetting Section (Word).docx | 04 Mar 2026 | References | Agency bypass detection — flag when referee is accountant/umbrella instead of agency | Medium | Complete | /api/check-reference-org detects accountant/umbrella keywords and warns | REQ-115
REQ-185 | An Intro to Vetting.docx | 04 Mar 2026 | Vetting | DBS certificate upload required when convictions are present | High | Complete | /action/flag-dbs-convictions route marks DBS as ON HOLD with upload requirement note | REQ-138
REQ-186 | OS1_Actions 12012026 copy.xlsx | 12 Jan 2026 | Dashboard | Dashboard custom metrics widgets — revenue forecasting, headcount trends, upcoming leavers count on main dashboard (R003) | Medium | Complete | Revenue Forecast Summary, Headcount Trend chart (6-month Chart.js line), Upcoming Leavers table added to dashboard below Open Jobs | Queries reuse revenue page logic
REQ-187 | OS1_Actions 12012026 copy.xlsx | 12 Jan 2026 | Projects | Engagement plan integration flow — auto-create jobs from plan roles; plan-driven revenue targets (R006) | Medium | Complete | POST /engagement/<id>/auto-create-jobs route; plan save flash includes Auto-Create Jobs button for missing roles | Jobs created with role_type, title, public_token, salary from plan pay_rate
REQ-188 | OS1_Actions 12012026 copy.xlsx | 12 Jan 2026 | Resource Pool | Candidate list column configuration — user-configurable visible columns and ordering (R014) | Medium | Complete | Columns dropdown with checkboxes toggles table column visibility; preferences saved to localStorage | Pure JS, no backend changes
REQ-189 | OS1_Actions 12012026 copy.xlsx | 12 Jan 2026 | Vetting | Vetting information fallback table — manual data entry when Verifile API unavailable or for legacy/offline check results (R022) | Medium | Complete | POST /candidate/<id>/vetting-manual route; modal form in application_detail.html with check type, status, result, reference, date, notes | Manual Entry button on vetting section header
REQ-190 | OS1_Actions 12012026 copy.xlsx | 12 Jan 2026 | Reporting | Reporting/MI page — dedicated reporting section with fill rates, time-to-hire, conversion rates, exportable management reports (R024) | High | Complete | GET /reporting route + reporting.html template with fill rate table, pipeline conversion funnel chart, application volume line chart, vetting donut, time-to-hire table, CSV export | Added to sidebar nav
REQ-191 | OS1_Actions 12012026 copy.xlsx | 12 Jan 2026 | Dashboard | Dashboard KPI tiles clickable — click-through to filtered views (e.g. Live Engagements → engagement list, Vetting → workflow) (R001) | Low | Complete | KPI tiles now have onclick handlers: Live Engagements→engagements, Delivery Target→workflow, Associates Offered→workflow?stage=offered, Vetting→workflow?stage=ready_to_contract, Contracted→placements | Cursor pointer + link icon indicator
REQ-192 | OS1 Wireframe_Backend Ian version copy.docx | 19 Feb 2026 | Resource Pool | True postcode radius search using geocoding (currently outcode-only prefix matching) | Medium | Complete | _geocode_postcode() + _haversine_miles() helpers using postcodes.io bulk API; batch geocodes up to 100 postcodes at a time; falls back to outcode match if geocoding fails | Free API, no key needed
REQ-193 | OS1_Actions 12012026 copy.xlsx | 12 Jan 2026 | Workflow | Admin-configurable workflow stages — rename, reorder, add, remove stages (currently 9 hardcoded stages) (R008) | Medium | Not Started | StageConfig model + read-only admin view exist. Editing DISABLED: 9 stages are tightly coupled to auto-transition logic (vetting→Contract Issued, e-sign→Contract Signed). Full decoupling refactor required before editing can be enabled. | See C-8 contradiction. Admin page is read-only.
REQ-194 | OS1_Actions 12012026 copy.xlsx | 12 Jan 2026 | Workflow | General skip/unskip stage functionality for all workflow stages (currently interview-only) (R018) | Medium | Complete | POST /action/skip_stage/<id> and /action/unskip_stage/<id> routes; workflow.html cards have dropdown with Skip to.../Move back to... options for all stages | Audit logged

## Summary
OS1 Requirements Summary
Total Requirements: 194
Status | Count | %
Complete | 193 | 99.5%
Not Started | 1 | 0.5%
Category | Total | Complete | Remaining
Admin | 5 | 5 | 0
Associate Portal | 38 | 38 | 0
Associate Profile | 4 | 4 | 0
Dashboard | 3 | 3 | 0
Documents | 8 | 8 | 0
Login | 1 | 1 | 0
Placements | 12 | 12 | 0
Projects | 14 | 14 | 0
References | 18 | 18 | 0
Reporting | 1 | 1 | 0
Resource Pool | 11 | 11 | 0
Revenue | 3 | 3 | 0
Security | 9 | 9 | 0
Timesheets | 12 | 12 | 0
Vetting | 37 | 37 | 0
Workflow | 18 | 17 | 1

## Contradictions
ID | Description | Documents in Conflict | Recommended Resolution | Status
C-1 | Vetting trigger: manual vs automatic. Feedback says manual button needed. Vetting Section says auto-load requirements. | OS1Feedback.xlsx vs Vetting Section (Word).docx | Auto-create checks as WAITING FOR ASSOCIATE when candidate added to project. Manual Start Vetting button fires API calls and sends email. | Complete
C-2 | 'Waiting External' status — document says likely unnecessary as it duplicates In Progress. | Vetting Section (Word).docx (internal) | Not adding. Document itself recommends skipping. | Complete
C-3 | Declaration auto-hold: On Hold vs Flagged. If vetting grid exists → On Hold. If pre-vetting → Flag only. | Vetting Section (Word).docx (internal) | Dual behaviour: Yes answer → if VettingChecks exist, set all to ON HOLD + orange. If no grid yet, flag candidate for when vetting starts. | Complete
C-4 | Consent form delivery: e-sign primary (Signable) vs hand-signed edge case. | An Intro to Vetting.docx vs Consent Form.pdf | Primary flow via Signable e-sign. Manual upload fallback added for hand-signed forms (PDF upload saves as consent_signed document). | Complete
C-5 | Reference period: fixed 3 years vs configurable per client. | An Intro to Vetting.docx vs Vetting Section (Word).docx | Configurable per engagement via reference_period_years field (default 3). Editable in create/edit engagement forms. | Complete
C-6 | Umbrella companies: fixed 2 named (PayStream + Trafalgar) vs open panel. | OS1_Associate Portal_v1.0.pptx vs An Intro to Vetting.docx | Configurable admin panel (ApprovedUmbrella model + CRUD). Pre-seeded with PayStream + Trafalgar + Limited Company. Portal reads dynamically with hardcoded fallback. | Complete
C-7 | 'Placed' column in workflow vs grid removal rules. Different views — no actual conflict. | OS1Feedback.xlsx vs Vetting Section (Word).docx | Already resolved. Placed column removed from resourcing workflow per feedback. Grid removal rule applies to vetting workflow only. No conflict. | Complete